## Greenbelt Project Plan

Project: Greenbelt Reparations Commission
Timeframe: Next Two Weeks

### Objectives

- Finalize project requirements by meeting with the Greenbelt Reparations Commission.

- Gather and clean demographic data from Census.gov and the Maryland Department of Education.

- Begin developing GIS-based visualizations to map demographic changes.

- Address technical and data-related risks identified in the internal risk assessment.

### Key Activities & Responsibilities

#### A. Client Meeting & Requirements Gathering (Lead: Elise Ferguson)

- Schedule and conduct a virtual meeting with Bob Rand and the Greenbelt Reparations Commission.

- Clarify project expectations, including:

  - Preferred demographic trends and historical focus.

  - Preferred visualization formats (GIS maps).

  - Data sources and key milestones.

- Document key takeaways and update the project scope accordingly.

- Deliverable: Meeting summary with refined project requirements.

#### B. Data Collection & Cleaning (Lead: Emmanuel Ephraim)

- Obtain census and education data for the past four decades.

- Cross-check data sources for accuracy and completeness.

- Format data for compatibility with GIS software.

- Deliverable: Structured, cleaned dataset ready for GIS mapping.

#### C. GIS Mapping & Visualization Development (Leads: Khoa Do)

- Set up GIS software and accounts

- Begin developing demographic maps by census tract or ZIP Code

- Create initial test visualizations to assess clarity and effectiveness.

- Deliverable: Prototype GIS visualizations of demographic shifts.

#### D. Risk Mitigation & Technical Troubleshooting (Lead: Fariha Prapti)

- Identify and address technical challenges related to GIS tools and large datasets.

- Consult university faculty for assistance with historical data sources.

- Explore alternative visualization tools if GIS proves too complex or limited.

- Deliverable: Risk mitigation update with solutions for identified challenges.

### Timeline & Milestones

| Task | Responsible | Week1 | Week2 | Deliverable |
| --- | --- | --- | --- | --- |
| Schedule and conduct client meeting | Elise Ferguson | ✔ | ✔ | Meeting summary |
| Document client expectations | Ruchir Kasineni | ✔ | ✔ | Refined project scope |
| Collect and clean demographic data | Emmanuel Ephraim | ✔ |  | Structured dataset |
| Set up GIS software and accounts | Khoa Do | ✔ |  | GIS-ready setup |
| Develop initial GIS visualizations | Fariha Prapti | ✔ |  | Prototype maps |
| Identify and address technical risks | Fariha Prapti |  |  | Risk mitigation update |

### Potential Challenges & Solutions

| Risk Category | Impact | Likelihood | Proposed Solution |
| --- | --- | --- | --- |
| Inaccurate or incomplete data | High | Medium | Cross-check data with multiple sources |
| GIS software limitations | High | High | Research and test alternative tools |
| Difficulty accessing historical demographic data | Medium | High | Consult faculty or research librarians for guidance |
| Data visualization performance issues | Medium | Medium | Optimize dataset for efficient processing |
| Limited stakeholder feedback | Medium | High | Maintain clear communication and meeting follow-ups |

### 5. Next Steps

- Finalize the client meeting schedule and prepare discussion points.

- Begin data collection and cleaning while ensuring accuracy.

- Set up GIS tools and begin initial visualization development.

- Provide an internal project update at the end of two weeks.

### 6. Conclusion

This plan outlines the critical steps for the next two weeks to ensure steady progress toward creating meaningful GIS-based visualizations for the Greenbelt Reparations Commission. By closely managing risks, maintaining client engagement, we aim to deliver high-quality results..